Sample Timeline

Here is a sample timeline to help you think through the sequence of planning your Strolling Thunder event.

8 Weeks Out or More

- Confirm your Strolling Thunder date and location

- Begin engaging priority partners to participate

7 Weeks Out

- Identify the policymakers with whom you want to meet

- Begin identifying families to participate in Strolling Thunder

- Conduct outreach to reporters to announce Strolling Thunder

- Announce Strolling Thunder on social media

- Continue engaging partners to participate

6 Weeks Out

- Continue identifying families to participate in Strolling Thunder

- Continue engaging partners to participate

- Confirm collateral materials needs and begin developing materials

- Build excitement for the event on social media

5 Weeks Out

- Finalize families who will participate in Strolling Thunder and help them think through the stories they want to tell their policymakers

- Finalize partnership commitments around Strolling Thunder

- Continue to build excitement for the event on social media

4 Weeks Out

- Begin outreach to schedule meetings with policymakers

- Begin conducting earned media outreach to pitch families’ stories to local reporters

- Continue to build excitement for the event on social media

3 Weeks Out

- Continue outreach to schedule meetings with policymakers

- Continue to conduct earned media outreach to pitch families’ stories to local reporters

- Draft an op-ed (with partners as appropriate)

- Continue to build excitement for the event on social media

- Encourage families to begin social media posting

2 Weeks Out

- Continue outreach to schedule meetings with policymakers

- Continue to build excitement for the event on social media

- Continue to encourage families to post to social media

- Finalize the op-ed

1 Week Out

- Tease Strolling Thunder on social media

- Distribute social media materials to partners to conduct outreach

- Continue to build excitement for the event on social media

- Pitch the op-ed

Week of Strolling Thunder

- Conduct training with families ahead of their policymaker meetings

- Hold policymaker meetings to educate them on issues important to infants, toddlers, and families

- Conduct earned and social media outreach around Strolling Thunder

- Thank policymakers via social media for holding meetings with families during Strolling Thunder

1-2 Weeks Following Strolling Thunder

- Send formal thank you notes to policymakers for meeting with families during Strolling Thunder, highlighting any media coverage.

- Thank families for participating in Strolling Thunder

- Thank partners for participating in Strolling Thunder

- Highlight results from Strolling Thunder via social media and in follow up media outreach